## Risk Register
PROJECT HELIX — PRODUCT QUALITY RISK REGISTER
GenomeBridge Clinical Systems Ltd ¦ Phase 1 — Quality Discovery ¦ Version 1.0 ¦ 4 August 2026
Risk ID | Category | Risk Statement | Affected Workflow Step | User Impact | Likelihood (1–5) | Impact (1–5) | Risk Score (L×I) | RAG | Proposed Control | Testing Layer | Owner | Status | Phase 1 Evidence | DCB0129/ 0160 Link | Notes
QR-001 | Patient Identification | Users search for a patient and select the wrong record because names or DOBs are similar | Step 1 — Locate patient | Incorrect patient receives clinical referral or genomic test order | 4 | 5 | 20 | HIGH | Enforce multi-field search returning DOB, gender and identifier alongside name; add confirmation step before record is opened | Exploratory (Phase 2) + Playwright Journey 1 (Phase 6) | Laura Okafor | Open | Observed in OpenMRS: search returns multiple results with similar surnames | DCB0129 §6.3 — Hazard: wrong patient selected | Priority 1 — feeds Phase 2 Charter 2
QR-002 | Duplicate Records | Two records are created for the same patient — one from registration, one from referral import | Step 1 — Register patient | Duplicate referrals, split history, incorrect cumulative reporting | 4 | 4 | 16 | HIGH | Implement pre-registration duplicate-check using FHIR conditional-create (if-none-exist); SQL uniqueness validation in Phase 4 | Exploratory (Phase 2) + FHIR API Phase 3 + SQL Phase 4 | Aisha Rahman | Open | HAPI FHIR: conditional-create tested in Phase 3 | DCB0129 §6.3 — Hazard: duplicate patient identity | Phase 3 task: POST Patient with If-None-Exist header
QR-003 | Incomplete Demographics | Patient records are created with mandatory demographic fields missing — name, DOB or gender absent | Step 2 — Review demographics | Downstream referral validation fails; reports exclude patients | 3 | 4 | 12 | MED | Enforce required fields in registration form; SQL completeness checks in Phase 4 | Cypress validation suite (Phase 5) + SQL Phase 4 | Mark Evans | Open | OpenMRS registration form explored in Phase 2 charter 3 | None direct | Boundary-value analysis on DOB field — Phase 2 task
QR-004 | Consent Handling | Genomic test request is created without a recorded consent resource | Step 4 — Record consent | Regulatory non-compliance; test request legally invalid | 3 | 5 | 15 | MED | Validate FHIR Consent resource is present and linked before ServiceRequest status advances; Phase 3 relationship validation | FHIR API Phase 3 + Playwright API Phase 3 | Laura Okafor | Open | FHIR Consent created and linked in Phase 3 workflow chain | DCB0129 §6.3 — Hazard: consent not obtained | CONS-MISS code in operational queue report
QR-005 | Referral Completeness | ServiceRequest records are submitted with one or more mandatory clinical fields absent | Step 3 — Create referral | Referral cannot be processed; TAT clock starts incorrectly | 4 | 4 | 16 | HIGH | FHIR schema validation for ServiceRequest mandatory fields in Phase 3; negative-test suite | FHIR API negative tests (Phase 3) + SQL Phase 4 | Aisha Rahman | Open | REF-INC code observed in operational data | None direct | Feeds wrong-direction trap: surface metric is TAT; root cause is REF-INC rate
QR-006 | Specimen Linkage | Specimen resource is created but not correctly associated with its parent ServiceRequest | Step 6 — Associate specimen | Genomic test cannot proceed; specimen appears orphaned in queue | 5 | 5 | 25 | HIGH | FHIR Specimen.request reference validation in Phase 3; SQL orphan-specimen check in Phase 4; SPEC-UNLINK rate tracked in operational report | FHIR API Phase 3 + SQL Phase 4 + Playwright API Phase 3 | Daniel Brooks | Open | SPEC-UNLINK is the primary metric thread across all phases | DCB0129 §6.3 — Hazard: wrong specimen used | PRIMARY RISK — answer key metric lives here
QR-007 | Workflow Status Tracking | Task resource status is not updated when processing moves between stages — WF-STALL accumulates | Step 7 — Track status | Operational team cannot identify blocked referrals; SLA breached silently | 3 | 4 | 12 | MED | Task status transition validation in Phase 3 API tests; WF-STALL count tracked in SQL Phase 4 | FHIR API Phase 3 + SQL Phase 4 | Aisha Rahman | Open | WF-STALL code in operational report | None direct | Phase 4 SQL: invalid status transitions represented in dataset
QR-008 | Diagnostic Report Availability | DiagnosticReport resource is created but not linked to the correct patient or subject | Step 8 — Diagnostic report | Clinician retrieves wrong report or report is inaccessible | 2 | 5 | 10 | MED | FHIR DiagnosticReport.subject reference validation in Phase 3 | FHIR API Phase 3 | Laura Okafor | Open | DiagnosticReport relationship tested in Phase 3 chain | DCB0129 §6.3 — Hazard: wrong result attributed | Low likelihood — tested for completeness of hazard coverage
QR-009 | Unauthorised Access | A user in one role can access a patient record or referral they should not see | Step 9 — Access control | Patient confidentiality breach; UK GDPR Article 5(1)(f) violation | 2 | 5 | 10 | MED | Role-based workflow exploration in Phase 2 charter 7; access-control scenarios in Playwright Phase 6 | Exploratory Phase 2 + Playwright Phase 6 | Laura Okafor | Open | OpenMRS role exploration in Phase 2 | DCB0160 §8 — Deploying organisation access controls | Awareness only — cannot perform security testing against public system
QR-010 | Session Control | An authenticated session does not terminate correctly on logout or timeout | Step 9 — Session | Subsequent user on shared terminal accesses prior session | 3 | 4 | 12 | MED | Session and logout tests in Playwright Journey 4 Phase 6; Cypress session checks Phase 5 | Cypress Phase 5 + Playwright Phase 6 | Mark Evans | Open | Logout and session recovery tested in Phase 2 charter 1 | None direct | Safely testable on public demo environment
QR-011 | Form Validation Inconsistency | Validation messages are absent, inconsistent or misleading across registration and referral forms | Steps 1–3 | Users submit incomplete data believing it was accepted; support ticket volume increases | 4 | 3 | 12 | MED | Cypress validation suite Phase 5 — equivalence partitioning and boundary-value analysis applied | Cypress Phase 5 | Mark Evans | Open | Phase 2 charter 3 and 5 — validation behaviour documented | None direct | James Wright complaint theme — form validation issues
QR-012 | API Compatibility | A change to the FHIR API contract removes or renames a field, breaking downstream consumers | Steps 3–8 — all API consumers | Consumers silently receive null where a value is expected; data loss | 2 | 4 | 8 | LOW | API compatibility analysis in Phase 3 — fictional old vs new contract diff | FHIR API Phase 3 | Aisha Rahman | Open | Compatibility assessment document produced in Phase 3 | None direct | Backwards-compatibility risk analysis — no live Pact environment required
QR-013 | Synthetic Data Protection | A synthetic record is created with a format indistinguishable from real patient data | All phases — test data | GDPR breach risk; regulatory non-compliance under UK DSPT | 2 | 5 | 10 | MED | Synthetic data policy produced in Phase 4; naming convention and tagging enforced | SQL Phase 4 — data policy + naming convention | Laura Okafor | Open | Laura Okafor constraint — non-negotiable | UK GDPR Article 5 + NHS DSPT | CONS-MISS and SPEC-UNLINK codes must not reference real identifiers
QR-014 | Accessibility | Key clinical workflows are inaccessible to users relying on keyboard navigation or assistive technology | Steps 1–3 — patient search and registration | Clinical staff with accessibility needs cannot complete referral workflow | 3 | 3 | 9 | MED | axe-core checks on login, search, registration, error states in Playwright Phase 6; keyboard-only charter in Phase 2 | Exploratory Phase 2 + Playwright Phase 6 (axe-core) | Daniel Brooks | Open | Phase 2 charter 7 — keyboard-only workflow | WCAG 2.1 AA — not DCB0129 directly | Niche but recurring in UK healthtech QA postings
QR-015 | Browser Compatibility | A workflow behaves correctly in Chromium but fails or renders incorrectly in Firefox or WebKit | Steps 1–3 | Clinical users on non-Chrome browsers experience broken workflows | 2 | 3 | 6 | LOW | Playwright cross-browser Phase 6 — Journey 3 runs in Chromium, Firefox and WebKit | Playwright Phase 6 | Mark Evans | Open | Phase 2 charter 8 — browser behaviour documented | None direct | Environmental failures must be distinguished from genuine defects
QR-016 | Automation Reliability | The existing Cypress suite produces intermittent failures caused by test design, not the application | All automated checks | False confidence in green build; real defects masked by flaky tests | 5 | 4 | 20 | HIGH | Phase 5 reliability measurement — first-run vs final pass rate; flaky-test root-cause analysis | Cypress Phase 5 — reliability analysis | Mark Evans | Open | Mark Evans handover acknowledges inconsistent standards | None direct | Phase 5 allocation matrix determines what stays vs moves to Playwright
QR-017 | Public Environment Instability | OpenMRS or HAPI FHIR public demo server is unavailable or resets data during a test run | All browser and API tests | Test results are invalid; CI pipeline reports false failures | 3 | 3 | 9 | MED | Tests create own data dynamically; avoid fixed IDs; tolerate resets; CI timeout controls; environment instability classified separately from product defects | All phases — responsible testing rules enforced | Daniel Brooks | Open | Documented in Phase 7 CI/CD failure classification | None direct | Section 2 of brief: candidate cannot rely on permanent data
QR-018 | Test Data Reuse | Automation tests share a fixed patient record — one test's state change breaks subsequent tests | Phases 5 and 6 — automation | Non-deterministic failures; order-dependent test results | 4 | 3 | 12 | MED | Phase 4 naming convention and unique-run identifiers applied in Cypress Phase 5 and Playwright Phase 6 | Phase 4 utilities + Cypress Phase 5 + Playwright Phase 6 | Mark Evans | Open | Phase 4 test-data policy defines isolation requirement | None direct | Directly addresses James Wright complaint about inconsistent regression results
QR-019 | Performance Under Load | The referral submission endpoint degrades unacceptably under expected concurrent user load | Step 3 — Create referral | Referral submission times out; clinical users abandon and retry creating duplicates | 2 | 4 | 8 | LOW | k6 performance tests against local mock endpoint in Phase 7 — baseline, expected load, stress spike, recovery | Phase 7 — k6 performance | Daniel Brooks | Open | Local mock only — must not load-test public systems | None direct | p50/p95/p99 latency thresholds defined in Phase 7
QR-020 | Quality Evidence Consolidation | Release decision is made based on raw test-pass count rather than risk-weighted quality evidence | Step — Release review | P1 defects ship to production because scorecard looked green | 3 | 5 | 15 | MED | Phase 8 final quality scorecard reconciles all phase evidence; Go/No-Go recommendation requires evidence per risk | Phase 8 — release readiness | Daniel Brooks | Open | Addresses GenomeBridge's stated problem: 'release decisions rely too heavily on test count' | DCB0129 §9 — release authorisation requires documented evidence | Senior-stretch deliverable — Phase 8
QR-021 | Clinical Safety Context | QA evidence is presented to clinical safety reviewers without distinguishing what it does and does not prove | All phases — reporting | Clinical Safety Officer makes assurance decisions on insufficient evidence | 2 | 5 | 10 | MED | Phase 1 system context map distinguishes QA evidence from clinical safety case; Phase 8 Laura Okafor challenge response addresses this directly | Phase 1 + Phase 8 | Laura Okafor | Open | DCB0129/DCB0160 awareness documented in company brief | DCB0129 §6 and DCB0160 §8 — clinical safety case ownership | Awareness-level only — candidate is NOT the Clinical Safety Officer
QR-022 | Traceability | Test results cannot be traced back to requirements or risks — release decision is not auditable | All phases | Cannot demonstrate that priority risks were tested; audit fails | 3 | 4 | 12 | MED | Requirements traceability matrix built in Phase 1; updated each phase; final matrix in Phase 8 | All phases — traceability matrix | Daniel Brooks | Open | Traceability matrix column present in this register | DCB0129 §9 — traceability of safety-relevant testing | Cross-phase artefact — connects risk IDs to test IDs to evidence

## Risk Summary
PROJECT HELIX — RISK SUMMARY DASHBOARD
RAG Status |  | Risks by Category | Count
HIGH (≥16) | 5 | API Compatibility | 1
MEDIUM (9–15) | 14 | Accessibility | 1
LOW (<9) | 3 | Automation Reliability | 1
TOTAL RISKS | 22 | Browser Compatibility | 1
|  | Clinical Safety Context | 1
|  | Consent Handling | 1
|  | Diagnostic Report Availability | 1
|  | Duplicate Records | 1
|  | Form Validation Inconsistency | 1
|  | Incomplete Demographics | 1
|  | Patient Identification | 1
|  | Performance Under Load | 1
|  | Public Environment Instability | 1
|  | Quality Evidence Consolidation | 1
|  | Referral Completeness | 1
|  | Session Control | 1
|  | Specimen Linkage | 1
|  | Synthetic Data Protection | 1
|  | Test Data Reuse | 1
|  | Traceability | 1
|  | Unauthorised Access | 1
|  | Workflow Status Tracking | 1

## Test Layer Matrix
PROJECT HELIX — TEST LAYER DECISION MATRIX
Risk ID | Risk Statement (short) | Manual Exploratory | Cypress | Playwright | FHIR API (Postman/PW) | SQL Validation | Performance (k6)
QR-001 | Wrong patient selected | ✓ |  | ✓
QR-002 | Duplicate patient records | ✓ |  |  | ✓ | ✓
QR-003 | Incomplete demographics | ✓ | ✓ |  |  | ✓
QR-004 | Consent not recorded |  |  |  | ✓
QR-005 | Referral incomplete (REF-INC) |  |  |  | ✓ | ✓
QR-006 | Specimen unlinked (SPEC-UNLINK) |  |  |  | ✓ | ✓
QR-007 | Workflow stalled (WF-STALL) |  |  |  | ✓ | ✓
QR-008 | Diagnostic report mislinked |  |  |  | ✓
QR-009 | Unauthorised access | ✓ |  | ✓
QR-010 | Session not terminated | ✓ | ✓ | ✓
QR-011 | Form validation inconsistency | ✓ | ✓
QR-012 | API compatibility break |  |  |  | ✓
QR-013 | Synthetic data unprotected |  |  |  |  | ✓
QR-014 | Accessibility barriers | ✓ |  | ✓
QR-015 | Browser incompatibility | ✓ |  | ✓
QR-016 | Flaky automation (Cypress) |  | ✓
QR-017 | Public environment instability | ✓ | ✓ | ✓ | ✓
QR-018 | Test data reuse causing failures |  | ✓ | ✓ |  | ✓
QR-019 | Performance degradation | [5 empty] | ✓
QR-020 | Evidence not consolidated
QR-021 | Clinical safety context gap | ✓
QR-022 | Traceability gap | ✓